{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["Cover","Quelldaten","Aktivitäten"],"not_rendered":{"charts":1,"images":0,"macros":1,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Cover","index":0,"n_rows":23,"n_cols":3,"rows_kept":23,"cut":false,"hidden":false,"merged":[]}
[]
[]
[null,"Excel in Perfektion"]
[]
[]
[]
[null,"Kapitel",11]
[null,"Thema","Prozesse organisieren"]
[]
[null,"Inhalt","Gantt-Diagramm"]
[]
[null,null," "]
[]
[]
[]
[]
[]
[null,"Version","5.0"]
[null,"Autor","Harald Nahrstedt"]
[null,"Letzte Bearbeitung","2026-06-09"]
[]
[]
[null,"Springer Vieweg Verlag"]

{"sheet":"Quelldaten","index":1,"n_rows":10,"n_cols":4,"rows_kept":10,"cut":false,"hidden":false,"merged":[]}
["Aktivität","Starttermin","Dauer","Endtermin"]
[" 2 Materialbestellung","2026-06-09",3,{"$f":"B2+C2","v":"2026-06-12"}]
[" 3 Arbeitsplanung","2026-06-09",5,"2026-06-14"]
[" 4 Materialkosten",{"$f":"D2","v":"2026-06-12"},4,"2026-06-16"]
[" 5 Materiallieferung",{"$f":"D2","v":"2026-06-12"},7,"2026-06-19"]
[" 6 Personalschulung",{"$f":"D3","v":"2026-06-14"},4,"2026-06-18"]
[" 7 Lohnkosten",{"$f":"D3","v":"2026-06-14"},5,"2026-06-19"]
[" 8 Selbstkosten",{"$f":"D4","v":"2026-06-16"},5,"2026-06-21"]
[" 9 Fertigung",{"$f":"D5","v":"2026-06-19"},6,"2026-06-25"]
["10 Lieferung",{"$f":"D9","v":"2026-06-25"},1,"2026-06-26"]

{"sheet":"Aktivitäten","index":2,"n_rows":10,"n_cols":4,"rows_kept":10,"cut":false,"hidden":false,"merged":[]}
["Aktivität","Starttermin","Dauer","Endtermin"]
[" 2 Materialbestellung","2026-06-09",3,{"$f":"B2+C2","v":"2026-06-12"}]
[" 3 Arbeitsplanung","2026-06-09",5,"2026-06-14"]
[" 4 Materialkosten",{"$f":"D2","v":"2026-06-12"},4,"2026-06-16"]
[" 5 Materiallieferung",{"$f":"D2","v":"2026-06-12"},7,"2026-06-19"]
[" 6 Personalschulung",{"$f":"D3","v":"2026-06-14"},4,"2026-06-18"]
[" 7 Lohnkosten",{"$f":"D3","v":"2026-06-14"},5,"2026-06-19"]
[" 8 Selbstkosten",{"$f":"D4","v":"2026-06-16"},5,"2026-06-21"]
[" 9 Fertigung",{"$f":"D5","v":"2026-06-19"},6,"2026-06-25"]
["10 Lieferung",{"$f":"D9","v":"2026-06-25"},1,"2026-06-26"]